## Sheet1
Task name | Duration | Start | End | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Software Development
-- Initial Generator
-- Genetic Enhancer
-- Post-Processing
Software Engineering Design | 4 days
Procedural Modelling Rooms | 7 days
Procedural Linking Rooms using IK | 8 days
Implement Generic Algorithm | 10 days
Polish and Finalise | 4 days
Software testing
Demonstration
Preparation | 7 days
Rehearsing | 1 day
Presentation | 1 day
Write up
-- Interium Report
-- First Draft
-- Final Draft
Introduction | 14 days
Software Design | 30 days
Results and Discussion | 14 days
Proof-reading and polishing | 17 days
Bind Dissertation | 5 days